## all
| Working Hours | Meeting Hours | Total Hours
David | 95 | 39.5 | 134.5
Davy | 211.5 | 56 | 267.5
Erica | 51.25 | 32 | 83.25
Ibrahim | 92.5 | 46.5 | 139
Nich | 93.5 | 43 | 136.5
total | 543.75 | 217 | 760.75
average/person | 108.75 | 43.4 | 152.15
average/person/week | 7.1816 | 2.866 | 10.0476
number of weeks | 15.1429

## weekly
2010-01-01 | 2010-01-10 | 2010-01-17 | 2010-01-24 | 2010-01-31 | 2010-02-07 | 2010-02-14 | 2010-02-21 | 2010-02-28 | 2010-03-07 | 2010-03-14 | 2010-03-21 | 2010-03-28 | 2010-04-04 | 2010-04-11 | 2010-04-18 | 2010-04-25 | 2010-05-02 | 2010-05-09 | 2010-05-16
David | 12.5 | 7 | 4.5 | 7 | 8 | 4.5 | 22 | 3 | 10.5 | 3 | 2 | 3.5 | 14 | 27 | 10 | 0 | 0 | 0 | 0
Davy | 24.5 | 9.5 | 13 | 27 | 3.5 | 9.5 | 10.5 | 11.5 | 24.5 | 22.5 | 4 | 26.5 | 17.5 | 51 | 50.5 | 12 | 0 | 0 | 0
Erica | 8 | 5.5 | 4.75 | 6.75 | 9 | 0 | 0.5 | 6.5 | 7 | 21 | 1 | 4 | 7 | 6 | 3 | 0 | 0 | 0 | 0
Ibrahim | 8 | 7 | 8 | 13 | 6 | 5.5 | 1 | 6 | 9.5 | 22 | 8 | 4 | 7 | 21 | 18 | 0 | 0 | 0 | 0
Nich | 15 | 2 | 13 | 14 | 6.5 | 7.5 | 10 | 3.5 | 5 | 6.5 | 12 | 4 | 2.5 | 15 | 30 | 2 | 0 | 0 | 0

## david
Date | Hours | Comment
2010-01-05 | 1 | Weekly Meeting
2010-01-05 | 3 | Group Meeting
2010-01-07 | 3 | Group Meeting
2010-01-08 | 2 | Knex Party
2010-01-09 | 0.5 | Purchase Meccano
2010-01-09 | 3 | Meccano Party
2010-01-14 | 1 | Group Meeting
2010-01-14 | 1 | Deriving equations for tool position
2010-01-14 | 3 | Update Matlab model for PT1b
2010-01-14 | 1 | Simplified gravity comp fbd and rough software block diagram
2010-01-15 | 1 | Freebody diagrams on gravity compensation
2010-01-18 | 0.5 | Analysis of motor placement
2010-01-19 | 1 | Group Meeting
2010-01-19 | 1 | Weekly Meeting
2010-01-20 | 1 | Meeting with Nich on gravity compensation
2010-01-21 | 1 | Group Meeting
2010-01-26 | 2 | Group Meeting
2010-01-26 | 1 | Weekly Meeting
2010-01-28 | 1 | Group Meeting
2010-01-29 | 2 | Solid Modelling
2010-01-29 | 1 | Solid Modelling
2010-02-01 | 1 | Client pre-meeting
2010-02-01 | 1 | Client Meeting
2010-02-02 | 4 | Solid Modelling
2010-02-04 | 2 | Design Breakdown
2010-02-08 | 0.5 | Group Meeting
2010-02-08 | 1 | Weekly Meeting
2010-02-11 | 3 | Design and Decisions Meeting
2010-02-18 | 1 | Group Meeting on Skype
2010-02-19 | 12 | Solid Modeling of design (span of reading break)
2010-02-19 | 4 | Joint 1-2 design
2010-02-19 | 4 | Bearing selection and research for joint 1-2
2010-02-20 | 1 | Group Meeting on Skype
2010-02-23 | 3 | Group Meeting
2010-03-02 | 1.5 | Group Meeting
2010-03-02 | 1 | Weekly Meeting
2010-03-01 | 2 | Power supply research
2010-03-01 | 2 | Preliminary wiring harness design
2010-03-02 | 1 | Trying to understand the bone mount
2010-03-06 | 3 | Log book catch-up
2010-03-09 | 2 | Group Meeting
2010-03-09 | 1 | Weekly Meeting
2010-03-16 | 2 | Group Meeting
2010-03-23 | 2.5 | Group Meeting
2010-03-23 | 1 | Weekly Meeting
2010-03-30 | 1 | Weekly Meeting
2010-04-01 | 9 | Finalizing Design and Modelling
2010-04-02 | 4 | Documenting Design
2010-04-05 | 2 | Producing Manufacturing Drawings
2010-04-06 | 3 | Producing Manufacturing Drawings
2010-04-06 | 6 | Lathe Work
2010-04-07 | 3 | Producing Manufacturing Drawings
2010-04-08 | 4 | Lathe Work
2010-04-08 | 3 | Updating Models and Producing Manufacting Drawings
2010-04-09 | 2 | Lathe Work
2010-04-11 | 4 | Updating backed up models after models became corrupt
2010-04-12 | 1 | Listed parts w/ status and estimated time required to finish
2010-04-12 | 1 | Reviewed parts list to ensure everything has been ordered
2010-04-12 | 4 | Lathe Work
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0

## davy
Date | Hours | Comment
2010-01-02 | 3 | Review reference material (Plaskos Thesis)
2010-01-03 | 3 | Review reference material (Nikolai, 2008 Group)
2010-01-05 | 1 | Weekly Meeting
2010-01-05 | 3 | Group Meeting
2010-01-06 | 4 | PM - Meeting Preparation
2010-01-07 | 3 | Group Meeting
2010-01-08 | 1 | Knex Party
2010-01-08 | 3 | PM - Meeting Summary, Calendar Updates
2010-01-09 | 0.5 | Purchase Meccano
2010-01-09 | 3 | Meccano Party
2010-01-11 | 2 | Microcontroller research
2010-01-11 | 0.5 | PM - Meeting Preparation
2010-01-12 | 2 | Group Meeting
2010-01-12 | 1 | Weekly Meeting
2010-01-14 | 1 | Group Meeting
2010-01-17 | 3 | Control System Research
2010-01-19 | 1 | Group Meeting
2010-01-19 | 1 | Weekly Meeting
2010-01-21 | 1 | Group Meeting
2010-01-22 | 2 | TAR Research
2010-01-24 | 1.5 | CFP Update
2010-01-24 | 1.5 | PM - Meeting Preparation and Updates
2010-01-24 | 2 | TAR - electrical and software (matlab)
2010-01-25 | 4 | TAR - electrical and software
2010-01-26 | 2 | Group Meeting
2010-01-26 | 1 | Weekly Meeting
2010-01-26 | 4 | TAR - microcontroller minimum speed calculation
2010-01-27 | 6 | TAR - microcontroller speed simulation and writeup
2010-01-28 | 4 | TAR compilation
2010-01-28 | 1 | Group Meeting
2010-02-01 | 1 | Group Meeting - Chris meeting prep
2010-02-01 | 1 | Chris Meeting
2010-02-02 | 1.5 | Group Meeting
2010-02-08 | 1.5 | Group Meeting
2010-02-08 | 1 | Weekly Meeting
2010-02-11 | 3 | Design and Decision Meeting
2010-02-13 | 1.5 | Researched sterilizable motor
2010-02-14 | 0.5 | Encoder speed requirement calculation
2010-02-14 | 2 | Researched QNX installation methods and issues
2010-02-15 | 3 | Ordered control system components
2010-02-18 | 1 | Group Meeting on Skype
2010-02-18 | 0.5 | Gravity Compensation motor experiment
2010-02-20 | 1 | Group Meeting on Skype
2010-02-21 | 2.5 | QNX Setup
2010-02-22 | 4 | QNX Setup
2010-02-22 | 1 | Motor controller cables research
2010-02-23 | 3 | Group Meeting
2010-02-24 | 1 | Motor Testing
2010-03-02 | 1.5 | Group Meeting
2010-03-02 | 1 | Weekly Meeting
2010-03-03 | 8 | QNX GPIO debug
2010-03-04 | 2 | Group Meeting
2010-03-06 | 4 | QNX - Interrupts
2010-03-07 | 8 | QNX - Interrupts
2010-03-08 | 1 | RMA/ship motor/encoder
2010-03-08 | 5 | QNX - Interrupts
2010-03-09 | 2 | Group Meeting
2010-03-09 | 1 | Weekly Meeting
2010-03-10 | 4 | QNX - Interrupts/Encoder test
2010-03-12 | 1.5 | Encoder/motor controller interface order
2010-03-16 | 2 | Group Meeting
2010-03-19 | 2 | OMAP UART documentation
2010-03-22 | 3 | QNX 3D implementation design
2010-03-23 | 2.5 | Group Meeting
2010-03-23 | 1 | Weekly Meeting
2010-03-24 | 3.5 | Physical interface board design
2010-03-25 | 2 | QNX - Encoder Test
2010-03-26 | 0.5 | Skype Meeting
2010-03-26 | 6 | QNX - Encoder Test
2010-03-27 | 8 | QNX - Encoder Test
2010-03-30 | 1.5 | Group Meeting
2010-03-30 | 1 | Weekly Meeting
2010-04-02 | 2 | Beagleboard diagnostic
2010-04-03 | 5 | AVR-CAN interface
2010-04-04 | 8 | beagleboard avr-can interface
2010-04-05 | 8 | beagleboard avr-can interface
2010-04-06 | 1.5 | Group Meeting
2010-04-06 | 1 | Weekly Meeting
2010-04-07 | 6 | beagleboard avr-can interface
2010-04-08 | 2 | Group Meeting
2010-04-09 | 1 | buying parts for interface board
2010-04-09 | 6.5 | interface board soldering and assembly
2010-04-10 | 8 | interface board debug
2010-04-11 | 3 | pair programming with Erica
2010-04-11 | 6 | serial interface debug
2010-04-12 | 1 | Ordering encoder and misc parts
2010-04-12 | 7 | serial interface debug
2010-04-13 | 0.5 | Weekly Meeting
2010-04-13 | 5 | serial interface debug
2010-04-14 | 1 | Buying parts for AVR board
2010-04-14 | 5 | Soldering AVR interface board/making cables
2010-04-15 | 4 | Helping out with machining
2010-04-16 | 1 | Looking for enclosure material
2010-04-17 | 1 | PM - Plan of action
2010-04-17 | 4 | Final Report - digrams and writeup
2010-04-18 | 12 | Final Report editing, Poster design
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0

## erica
Date | Hours | Comment
2010-01-05 | 1 | Weekly Meeting
2010-01-07 | 3 | Group Meeting
2010-01-09 | 4 | Knee Implant Research
2010-01-12 | 2 | Weekly Meeting
2010-01-12 | 1 | Group Meeting
2010-01-14 | 1 | Group Meeting
2010-01-16 | 1.5 | Research Implant Company
2010-01-19 | 1 | Group Meeting
2010-01-19 | 1 | Weekly Meeting
2010-01-21 | 1 | Group Meeting
2010-01-24 | 1.75 | CFP Update/Edit
2010-01-26 | 1 | TAR - motor speed
2010-01-27 | 3 | TAR - motor speed
2010-01-28 | 1 | Group Meeting
2010-02-01 | 1 | Group Meeting - Chris meeting prep
2010-02-01 | 1 | Chris Meeting
2010-02-02 | 1.5 | Group Meeting
2010-02-03 | 2.5 | CFP Update/Edit
2010-02-06 | 3 | CFP Update and misc
2010-02-20 | 0.5 | Group Meeting on Skype
2010-02-23 | 2 | Group Meeting
2010-02-26 | 2.5 | Order Femurs
2010-02-28 | 2 | Experimental Procedure
2010-03-02 | 1 | Weekly Meeting
2010-03-04 | 2 | Group Meeting
2010-03-05 | 2 | Pseudocode writeup
2010-03-09 | 2 | Group Meeting
2010-03-09 | 1 | Weekly Meeting
2010-03-10 | 8 | QNX & protocol procedure
2010-03-11 | 7 | Hard Constrait Programming
2010-03-13 | 3 | Hard Constrait Programming
2010-03-16 | 1 | Group Meeting
2010-03-23 | 2.5 | Group Meeting
2010-03-23 | 1 | Weekly Meeting
2010-03-26 | 0.5 | Skype Meeting
2010-04-02 | 7 | Hard Constrait Programming
2010-04-06 | 1 | Weekly Meeting
2010-04-08 | 2 | Group Meeting
2010-04-11 | 3 | Pair Programming Hard Constraint
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0

## ibrahim
Date | Hours | Comment
2010-01-05 | 1 | Weekly Meeting
2010-01-07 | 3 | Group Meeting
2010-01-08 | 1 | K'Nex Meeting
2010-01-09 | 3 | Meccano Meeting at Nick's Place
2010-01-11 | 4 | CFP Motor, Gear and Positioning write-up
2010-01-12 | 2 | Group Meeting
2010-01-12 | 1 | Weekly Meeting
2010-01-19 | 1 | Group Meeting
2010-01-19 | 1 | Weekly Meeting
2010-01-21 | 1 | Group Meeting
2010-01-24 | 5 | Torque theta graphs and motor selction writeup for TAR
2010-01-26 | 2 | Group Meeting
2010-01-26 | 1 | Weekly Meeting
2010-01-27 | 4 | TAR - motor and torque
2010-01-28 | 1 | Group Meeting
2010-02-01 | 1 | Group Meeting - Chris meeting prep
2010-02-01 | 1 | Chris Meeting
2010-02-01 | 1 | encoder analysis
2010-02-02 | 1 | Group Meeting
2010-02-04 | 2 | Encoder Research
2010-02-08 | 1.5 | Group Meeting
2010-02-08 | 1 | Weekly Meeting
2010-02-11 | 3 | Design and Decision Meeting
2010-02-18 | 1 | Group Meeting on Skype
2010-02-22 | 3 | Motor controller cables order
2010-02-23 | 3 | Group Meeting
2010-03-02 | 1.5 | Group Meeting
2010-03-02 | 1 | Weekly Meeting
2010-03-04 | 2 | Group Meeting
2010-03-06 | 5 | Preliminary Offest Joint Design
2010-03-08 | 6 | Detailed Offset Link/Link5/Tool Mount Drawings
2010-03-09 | 2 | Group Meeting
2010-03-09 | 1 | Weekly Meeting
2010-03-09 | 3 | Session 1 with Dave (design and solidworks) - Markus Talk
2010-03-10 | 2 | Session 2 with Dave (design and solidworks)
2010-03-11 | 4 | Final Tool Mount/Offset Drawings and Part research/listing
2010-03-11 | 1 | Lecture in Scarfe
2010-03-12 | 3 | Final Tool Mount/Offset Drawings and Part research/listing cont'd
2010-03-16 | 2 | Group Meeting
2010-03-16 | 1 | Material Ordering
2010-03-18 | 2 | Fastener Ordering and checkup with Perry
2010-03-19 | 3 | Bearing ordering-chechup-switch-reordering
2010-03-23 | 2.5 | Group Meeting
2010-03-23 | 1 | Weekly Meeting
2010-03-26 | 0.5 | Skype Meeting
2010-03-30 | 1.5 | Group Meeting
2010-03-30 | 1 | Weekly Meeting
2010-04-01 | 4.5 | Machine Shop: Rotating Base cutting and milling
2010-04-06 | 7.5 | Machine Shop (extended hours): Rotating Base milling
2010-04-07 | 4.5 | Machine work, preparation, discussions, cleanup
2010-04-08 | 4.5 | Machine work, preparation, discussions, cleanup
2010-04-09 | 4.5 | Machine work, preparation, discussions, cleanup
2010-04-12 | 4.5 | Machine work, preparation, discussions, cleanup
2010-04-13 | 4.5 | Machine work, preparation, discussions, cleanup
2010-04-14 | 4.5 | Machine work, preparation, discussions, cleanup
2010-04-15 | 4.5 | Machine work, preparation, discussions, cleanup
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0

## nicholas
Date | Hours | Comment
2010-01-05 | 1 | Weekly Meeting
2010-01-05 | 3 | Group Meeting
2010-01-07 | 3 | Group Meeting
2010-01-07 | 2 | Winnowing Documentation
2010-01-08 | 2 | Knex Party
2010-01-09 | 3 | Meccano Party
2010-01-10 | 1 | Tool Research
2010-01-12 | 1 | Weekly Meeting
2010-01-19 | 1 | Group Meeting
2010-01-19 | 1 | Weekly Meeting
2010-01-19 | 3 | Physical Prototyping writeup
2010-01-20 | 1 | Meeting with David on gravity compensation
2010-01-21 | 1 | Group Meeting
2010-01-23 | 3 | TAR writeup
2010-01-24 | 3 | Gravity compensation model
2010-01-26 | 2 | Group Meeting
2010-01-26 | 1 | Weekly Meeting
2010-01-27 | 7 | TAR - gravity compensation
2010-01-28 | 1 | Group Meeting
2010-02-01 | 1 | Group Meeting - Chris meeting prep
2010-02-01 | 1 | Chris Meeting
2010-02-02 | 1.5 | Group Meeting
2010-02-04 | 3 | Design breakdown
2010-02-08 | 1.5 | Group Meeting
2010-02-08 | 1 | Weekly Meeting
2010-02-11 | 3 | Design and Decision Meeting
2010-02-14 | 1 | Rotating base design
2010-02-14 | 1 | Sizing calculations
2010-02-15 | 3 | Coupling selection
2010-02-18 | 1 | Group Meeting on Skype
2010-02-19 | 0.5 | Sizing calculations
2010-02-19 | 0.5 | Gear box calculations
2010-02-19 | 2 | Motor selection background
2010-02-20 | 1 | Group Meeting on Skype
2010-02-23 | 3 | Group Meeting
2010-02-23 | 0.5 | Maxon motor types
2010-03-04 | 2 | Group Meeting
2010-03-04 | 2 | Implant Review
2010-03-04 | 1 | Motor precision requirements
2010-03-09 | 1.5 | Group Meeting
2010-03-09 | 1 | Weekly Meeting
2010-03-14 | 4 | Previous documentation review
2010-03-15 | 2 | Final documentation structure
2010-03-16 | 2 | Group Meeting
2010-03-18 | 1 | TAR Review
2010-03-18 | 3 | Rotation gravity compensation spreadsheet for new design
2010-03-23 | 2.5 | Group Meeting
2010-03-23 | 1 | Weekly Meeting
2010-03-26 | 0.5 | Skype Meeting
2010-03-30 | 1.5 | Group Meeting
2010-03-30 | 1 | Weekly Meeting
2010-04-05 | 3 | Gravity comp. curves
2010-04-06 | 6 | Gravity comp write up
2010-04-06 | 1 | Testing procedure
2010-04-09 | 4 | Machining
2010-04-10 | 1 | Testing procedure
2010-04-12 | 4 | Machining
2010-04-13 | 4 | Machining
2010-04-15 | 4 | Machining
2010-04-16 | 4 | Final documentation
2010-04-17 | 12 | Final documentation
2010-04-18 | 2 | Final documentation
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0