## OVERALL
SUBSYSTEM | DESCRIPTION | CONNECTING SYSTEMS | CONNECTION COMPONENTS | STATUS
Bone mount | Attaches rotating base to bone (femur). Use Praxim bone mount | Femur, rotating base, gravity compensation motor | Bone mount pins to femur, 'Axel 1' supports rotating base and gravity compensation motor, rotating base support by sealed ball bearing press fit onto 'Axel 1', motor press fit onto axel | Waiting for drawings and sample
Rotating Base | Allows for rotation about bone mount and houses link 1, physical constraint and motors | Bone mount, primary link system, support link system | supported by ball bearing attached to 'Axel 1' | Rough design
Primary Link System | Combination of links 1 and 2 that provide primary structure and receive hard constraint | Rotating base, physical constraint, support link system, link 3 | PLS connects to rotating base through sealed ball bearing, link 1 and link 2 connect by 2 sealed ball bearings, PLS LINK 3 connected bysealed ball bearing | Semi- detailed - requires bearing choice and structural, tolerance, bearing placement, axel constraints analysis
Support Link System | Restrains link 3 to allow for linear motion, aligned at 90 degree angle to primary link system | Rotating base, primary link system, link 3 | SLS connects to rotating base through sealed ball bearing, support link 1 and link 2 connect by 2 sealed ball bearings, SLS LINK 3 connected bysealed ball bearing - must keep bearing tolerances high to minimize alignment error | Semi- detailed - requires bearing choice and structural, tolerance, bearing placement, axel constraints analysis
Physical constraint | Implement hard constraint on link 1 of primary link system. Activated by motor attached to the rotating base | Rotating base, primary link system, motor 1 | Physical constraint pin is in direct contact with PLS and is attached to motor with offset and spline | Semi- detailed - requires moment arm length and gearing
Gravity compensation System | Motor will implement anti-gravity torque, and is attached to rotating base. Motor shaft will attach to bone mount axel. (1) Rotational (2) linear compensation | primary link system, | GCS(1): Motor press fit onto Axel 1 GCS(2): Mounted onto Axel 2 and Axel 3 at rotational base and link 3. Cam attached to joint between link 1 and link 2 will vary spring force and constrain spring. | (1)Rough design, requires coupling between bone mount axel and motor and (2) requires spring constant and spring actuator
Link 3 | Attaches to primary link 2, support link 2 and offset links 4 and 5 to allow of various horizontal placements | primary link system, support link system, offset links | Link 3 connected with Axel 3 and sealed ball bearings to PLS and SLS. Link 3 and Offset link joint (Link 4) welded | Rough design - requires offset links and primary/support system to be designed first.
Offset Links | Connects to Link 3 and positions tool by attaching to tool mount | link 3, tool mount system | Link 4 and link 5 connected by Axel 4 and sealed ball bearing, link 5 and tool mount connected with sealed thrust bearing | We've got nothing
Tool Mount System | Provides two degrees of freedom for tool and ensures drill stays stationary WRT to link 5. | Offset links, tool | link 5 and tool mount connected with sealed thrust bearing, tool pinned into tool mount - mounts must be tool specific | Rough design - needs looking at
Tool | Mounts to tool mount system and is purchased | tool mount system, bone | specific tools must be used | Select tool and tool bit - ordering. What about a dremel?
Tool Tracking System | Encoders and other measure record position of joint 1, primary link system, link 4, and link 5 | Encoder 1: Hard constraint motor, Encoder 2: Support system joint 2, Encoder 3: joint between link 4 and link 5, Encoder 5: gravity compensation motor | each mounted to corresponding joint axel (shaft?) | Rough design - select encoders and incorporate into link designs
Cable Management System | Contains cables WRT to device to limit cables effect on device motion | Encoder 1 cables: none, Encoder 2 cables: support link system, Encoder 3 cables: primary link system, Encoder 4: none - all cables go to 'cable box' | combination of grooves and zap straps | We've got nothing. Must be considered before building
Control System Box | House power supply, controllers, other electronics | cable management system, actuating pedal | cable box | We've got nothing. Cardboard?
Actuating Pedal | Fix position of tool when not in use | control system box | not sure | Rough design - requires feasibility analysis
General Link Design | 33mm bearings placed
Note on D1: tubby: bearings, couplings

## Bearing Selection
Type of Bearing | Description | Application | Model | Size | Concerns
Double angular contact | Double angular contact provides both radial and thrust constraints and will allow for preloading | Combination link and cap design (bearings placed in cap) which is press fit into link. Encoder can be position both on link side or on cap side |  |  | Size (really big)
Needle and thrust | Needle provides radial loading and thrust for preload loading | pressed into link at needle section, axel comes up flush onto bearing casing and will fit snuggly into inner race | NXTN | 18mm (wide) by 14mm (radial) link:
| Needle provides radial loading and thrust for preload loading | pressed into link at needle section, axel comes up flush onto bearing casing and will fit snuggly into inner race | NKX10TN | 23mm (w) by 24mm (rad) with 19mm bore, shaft size: 10mm | will need wider links to achieve
Plain bearing
Tapered roller bearings |  |  |  |  | way too big