## Sheet1
SUBSYSTEM | DESCRIPTION | CONNECTING SYSTEMS | CONNECTION COMPONENTS | STATUS
Bone mount | Attaches rotating base to bone (femur). Use Praxim bone mount | Femur, rotating base, gravity compensation motor | Bone mount pins to femur, 'Axel 1' supports rotating base and gravity compensation motor, rotating base support by sealed ball bearing press fit onto 'Axel 1', motor press fit onto axel | Waiting for drawings and sample
Rotating Base | Allows for rotation about bone mount and houses link 1, physical constraint and motors | Bone mount, primary link system, support link system | supported by ball bearing attached to 'Axel 1' | Rough design
Primary Link System | Combination of links 1 and 2 that provide primary structure and receive hard constraint | Rotating base, physical constraint, support link system, link 3 | primary link system connects to rotating base through sealed ball bearing, link 1 and link 2 connect by 2 sealed ball bearings | Semi- detailed - requires bearing choice and structural, tolerance, bearing placement, axel constraints analysis
Support Link System | Restrains link 3 to allow for linear motion | Rotating base, primary link system, link 3 |  | Semi- detailed - requires bearing choice and structural, tolerance, bearing placement, axel constraints analysis
Physical constraint | Implement hard constraint on link 1 of primary link system. Activated by motor attached to the rotating base | Rotating base, primary link system, motor 1 |  | Semi- detailed - requires moment arm length and gearing
Gravity compensation System | Motor will implement anti-gravity torque, and is attached to rotating base. Motor shaft will attach to bone mount axel. (1) Rotational (2) linear compensation | primary link system, |  | (1)Rough design, requires coupling between bone mount axel and motor and (2) requires spring constant and spring actuator
Link 3 | Attaches to primary link 2, support link 2 and offset links 4 and 5 to allow of various horizontal placements | primary link system, support link system, offset links |  | Rough design - requires offset links and primary/support system to be designed first.
Offset Links | Connects to Link 3 and positions tool by attaching to tool mount | link 3, tool mount system |  | We've got nothing
Tool Mount System | Provides two degrees of freedom for tool and ensures drill stays stationary WRT to link 5. | Offset links, tool |  | Rough design - needs looking at
Tool | Mounts to tool mount system and is purchased | tool mount system, bone |  | Select tool and tool bit - ordering. What about a dremel?
Tool Tracking System | Encoders and other measure record position of joint 1, primary link system, link 4, and link 5 | Encoder 1: Hard constraint motor, Encoder 2: Support system joint 2, Encoder 3: joint between link 4 and link 5, Encoder 5: gravity compensation motor |  | Rough design - select encoders and incorporate into link designs
Cable Management System | Contains cables WRT to device to limit cables effect on device motion | Encoder 1 cables: none, Encoder 2 cables: support link system, Encoder 3 cables: primary link system, Encoder 4: none - all cables go to 'cable box' |  | We've got nothing. Must be considered before building
Control System Box | House power supply, controllers, other electronics | cable management system, actuating pedal |  | We've got nothing. Cardboard?
Actuating Pedal | Fix position of tool when not in use | control system box |  | Rough design - requires feasibility analysis
Note on D1: tubby: bearings, couplings